## Sheet1
BusTrackingMachanism
Date | Objective | Progress
31-Mar-2025 - 06-Apr-2025 | Week 1: Research and Setup
Goal: Establish the foundation.
Tasks:
2025-03-31 | Day 1-2: Research how GPS tracking works and explore APIs (e.g., Google Maps API). Review Python libraries like Flask/Django for backend development.
2025-04-02 | Day 3: Create a basic project folder structure on your laptop (include folders for frontend, backend, and database).
2025-04-03 | Day 4-5: Set up the tools needed for the project (install Flask/Django, Python, HTML editor, and MySQL database).
2025-04-05 | Day 6-7: Review tutorials on creating a simple Flask web app with database integration.
Time Commitment: 1-2 hours/day, flexible during weekends.
Week 2: Basic Frontend Design
Goal: Build the user interface.
Tasks:
07-Apr-2025 - 09-Apr-25 | Day 1-3: Design wireframes for the bus tracking interface (e.g., input field for bus number, map display, real-time tracking section).
2025-04-10 | Day 4-7: Code the frontend using HTML, CSS, and JavaScript. Focus on creating:
2025-04-10 | A clean and responsive design.
2025-04-11 | A navigation bar and footer.
2025-04-12 | A placeholder for displaying the map.
Time Commitment: 1-2 hours/day on weekdays, 4-5 hours on weekends.
Week 3: Backend Development
Goal: Set up the backend for handling user requests.
Tasks:
13-Apr-25 - 14-Apr-25 | Day 1-2: Design a basic Flask/Django app structure.
15-Apr-25 - 16-Apr-25 | Day 3-4: Code the API endpoints for:
2025-04-15 | Fetching bus routes from the database.
2025-04-16 | Handling GPS location updates.
17-Apr-25 - 19-Apr-25 | Day 5-7: Connect the backend to the frontend (via AJAX or Fetch API).
Time Commitment: 1-2 hours/day on weekdays, 4-5 hours on weekends.
Week 4: Google Maps Integration
Goal: Display real-time bus locations and routes on the map.
Tasks:
20-Apr-25 - 22-Apr-25 | Day 1-3: Explore Google Maps API (or alternatives like OpenStreetMap).
23-Apr-25 - 24-Apr-25 | Day 4-5: Write Python code to fetch and display bus locations on the map.
26-Apr-25 - 27-Apr-25 | Day 6-7: Test the integration and troubleshoot issues (e.g., incorrect locations or map loading errors).
Time Commitment: 1-2 hours/day on weekdays, 4-5 hours on weekends.
Week 5: GPS Data Simulation
Goal: Create mock GPS data for testing.
Tasks:
28-Apr-25 - 30-Apr-25 | Day 1-3: Write a script to simulate bus movement (generate random GPS coordinates or use real routes).
01-May-25 - 02-May-25 | Day 4-5: Test the simulated data with the map and tracking mechanism.
Day 6-7: Refine the simulation and ensure smooth updates on the interface.
Time Commitment: 1-2 hours/day on weekdays, 4-5 hours on weekends.
Week 6: Database Implementation
Goal: Store bus routes, user data, and tracking history.
Tasks:
Day 1-3: Design the database schema in MySQL (tables for bus routes, location updates, and users).
Day 4-5: Implement database integration with the backend (Python + MySQL).
Day 6-7: Test CRUD operations (Create, Read, Update, Delete) for database entries.
Time Commitment: 1-2 hours/day on weekdays, 4-5 hours on weekends.
Week 7: Final Integration and Debugging
Goal: Connect all components and ensure smooth functionality.
Tasks:
Day 1-3: Run end-to-end tests on the system:
Submit bus number → View routes → Display real-time tracking on map.
Day 4-5: Debug any issues in the frontend, backend, or database.
Day 6-7: Optimize the code and improve interface responsiveness.
Time Commitment: 1-2 hours/day on weekdays, 5-6 hours on weekends.
Week 8: Polishing and Documentation
Goal: Prepare for presentation and submission.
Tasks:
Day 1-2: Add finishing touches to the UI (e.g., loading animations, better styling).
Day 3-4: Write project documentation:
Project overview.
How to run the system.
Challenges faced and solutions implemented.
Day 5-7: Create a presentation/demo for your teacher and team.
Time Commitment: 1-2 hours/day on weekdays, flexible on weekends.
3D Maps Tours This workbook has 3D Maps tours available. Open 3D Maps to edit or play the tours.